## Dashboard
RAG Chat-with-PDF — Project Plan
8 weeks · 1 hour/day · 56 tasks · Owner: Sirajul Salekin Nowshad
Start date | 2026-10-25 | ← edit this; all task dates update
Summary
Total tasks | 56
Done | 28
In progress | 9
Blocked | 0
% complete | 50%
Hours planned | 56
Hours logged | 0
Planned finish | 2026-12-19
Today's task | Install dev tools
Next not-done task | Tune chunk size / top-k
Progress by week
Week | Phase | Tasks | Done | % Done | Hrs logged | Week starts
1 | Setup | 7 | 7 | 100% | 0 | 2026-10-25
2 | Extraction & Chunking | 7 | 7 | 100% | 0 | 2026-11-01
3 | Indexing & Retrieval | 7 | 4 | 57.14% | 0 | 2026-11-08
4 | LLM & UI Shell | 7 | 5 | 71.43% | 0 | 2026-11-15
5 | Web UI & Chat | 7 | 5 | 71.43% | 0 | 2026-11-22
6 | Auth & Privacy | 7 | 0 | 0% | 0 | 2026-11-29
7 | History & Providers | 7 | 0 | 0% | 0 | 2026-12-06
8 | Evaluation & Deploy | 7 | 0 | 0% | 0 | 2026-12-13
How to use
1. Set the Start date (yellow cell) — every task date recalculates.
2. Each day, open the Tasks sheet, do that day's task, then set Status (dropdown) and log Actual hrs.
3. Editable cells on Tasks: Status, Actual hrs, Notes (light-yellow columns). Everything else is the plan.
4. Buffer days (every 7th day) are for catching up — don't plan new work on them.
5. Record retrieval / accuracy tests in the Eval Log sheet — it becomes your evaluation chapter.
Formulas:
Week starts = C5+([Week]-1)*7

## Tasks
ID | Week | Day | Date | Phase | Task | Steps | Done when | Est. hrs | Status | Actual hrs | Notes
T01 | 1 | 1 | 2026-10-25 | Setup | Install dev tools | Install Node.js LTS, Git, Docker Desktop, VS Code. Run node -v, git --version, docker --version. | All 4 tools report a version | 1 | Done
T02 | 1 | 2 | 2026-10-26 | Setup | Create Next.js project | npx create-next-app (TypeScript, Tailwind, App Router, src/). Create GitHub repo, first push. | App runs on localhost:3000 and is on GitHub | 1 | Done
T03 | 1 | 3 | 2026-10-27 | Setup | Postgres + pgvector in Docker | docker-compose.yml with pgvector/pgvector:pg16 + volume. docker compose up. Run CREATE EXTENSION vector; | Extension shows in \dx | 1 | Done
T04 | 1 | 4 | 2026-10-28 | Setup | Set up Drizzle ORM | Install drizzle-orm, drizzle-kit, postgres driver. DATABASE_URL in .env (add .env to .gitignore). | drizzle-kit connects without error | 1 | Done
T05 | 1 | 5 | 2026-10-29 | Setup | Define database schema | Tables: users, documents, document_chunks (embedding vector(768)), conversations, messages. Run migration. | 5 tables exist in database | 1 | Done
T06 | 1 | 6 | 2026-10-30 | Setup | Gemini API test | Get API key from Google AI Studio, store in .env. Script sends 'hello' and prints reply. | Script prints Gemini reply | 1 | Done
T07 | 1 | 7 | 2026-10-31 | Setup | Buffer / review | Catch up on unfinished tasks. Clean code, update TODO.md, commit. | Week 1 complete & committed | 1 | Done
T08 | 2 | 8 | 2026-11-01 | Extraction & Chunking | PDF text extraction | Install unpdf. Write lib/extract.ts returning [{page, text}]. | Prints text per page for 1 PDF | 1 | Done
T09 | 2 | 9 | 2026-11-02 | Extraction & Chunking | Test extraction on 3 PDFs | Try lecture notes, research paper, scanned PDF. Detect empty pages / no-text PDFs. | Scanned PDF flagged as 'no text' | 1 | Done
T10 | 2 | 10 | 2026-11-03 | Extraction & Chunking | Text cleaning | Normalise whitespace, fix hyphenated line breaks, drop page headers/footers if simple. | Clean output on all 3 test PDFs | 1 | Done
T11 | 2 | 11 | 2026-11-04 | Extraction & Chunking | Chunker | lib/chunk.ts: ~600 tokens, 80 overlap, each chunk keeps page_number + chunk_index. | Chunks print with page numbers | 1 | Done
T12 | 2 | 12 | 2026-11-05 | Extraction & Chunking | Test chunker | Small test with known text; log chunk count per PDF. | Chunk counts look sensible | 1 | Done
T13 | 2 | 13 | 2026-11-06 | Extraction & Chunking | Embedding function | lib/embed.ts using Gemini embedding model at 768 dims. Batch requests, handle rate limits. | Returns 768-length vectors | 1 | Done
T14 | 2 | 14 | 2026-11-07 | Extraction & Chunking | Buffer / review | Catch up, refactor, commit. | Week 2 complete & committed | 1 | Done
T15 | 3 | 15 | 2026-11-08 | Indexing & Retrieval | Ingestion script | scripts/ingest.ts: extract → chunk → embed → insert into documents + document_chunks. | Chunks with vectors stored in DB | 1 | Done
T16 | 3 | 16 | 2026-11-09 | Indexing & Retrieval | HNSW index | Add HNSW index (vector_cosine_ops) on embedding. Verify with EXPLAIN. | Index used in query plan | 1 | In Progress
T17 | 3 | 17 | 2026-11-10 | Indexing & Retrieval | Similarity search | lib/search.ts: embed question, return top-5 chunks by cosine distance with page numbers. | Terminal shows top-5 chunks + pages | 1 | Done
T18 | 3 | 18 | 2026-11-11 | Indexing & Retrieval | Retrieval test (10 questions) | Write 10 questions for a known PDF. Log in Eval Log sheet whether correct page is in top-5. | 10 rows in Eval Log | 1 | Done
T19 | 3 | 19 | 2026-11-12 | Indexing & Retrieval | Tune chunk size / top-k | Try 400 vs 600 vs 800 tokens and k=3/5. Record hit rate. | Best settings chosen & noted | 1 | Not Started
T20 | 3 | 20 | 2026-11-13 | Indexing & Retrieval | Grounded prompt design | System prompt: answer ONLY from passages, cite [doc, p.X], say 'not found' if missing. | Prompt saved in lib/prompts.ts | 1 | Done
T21 | 3 | 21 | 2026-11-14 | Indexing & Retrieval | Buffer / review | Catch up, commit. | Week 3 complete & committed | 1 | Not Started
T22 | 4 | 22 | 2026-11-15 | LLM & UI Shell | AI provider adapter | lib/ai/: generateAnswer() interface + Gemini implementation. | Adapter returns an answer | 1 | Done
T23 | 4 | 23 | 2026-11-16 | LLM & UI Shell | CLI question answering | scripts/ask.ts: question → search → prompt → answer with citations. | Cited answer in terminal | 1 | Done
T24 | 4 | 24 | 2026-11-17 | LLM & UI Shell | Test 'not found' fallback | Ask 5 off-topic questions; model must refuse rather than invent. | 5/5 return 'not found' | 1 | In Progress
T25 | 4 | 25 | 2026-11-18 | LLM & UI Shell | Structured citations | Parse/return citations as {documentId, page} alongside answer text. | JSON with answer + citations | 1 | Done
T26 | 4 | 26 | 2026-11-19 | LLM & UI Shell | UI shell with shadcn/ui | Init shadcn/ui. Dashboard layout: sidebar + main area. | Layout renders | 1 | Done
T27 | 4 | 27 | 2026-11-20 | LLM & UI Shell | Upload API route | Validate PDF type & size; save to ./storage/documents/<uuid>.pdf (outside /public). | File saved with generated ID | 1 | Done
T28 | 4 | 28 | 2026-11-21 | LLM & UI Shell | Buffer / review | Catch up, commit. | Week 4 complete & committed | 1 | Not Started
T29 | 5 | 29 | 2026-11-22 | Web UI & Chat | Ingest on upload | Run ingestion after upload; status = processing / ready / failed. | Status updates in DB | 1 | Done
T30 | 5 | 30 | 2026-11-23 | Web UI & Chat | Documents list page | Show user's PDFs with name, pages, status, date. | List shows uploaded PDFs | 1 | Done
T31 | 5 | 31 | 2026-11-24 | Web UI & Chat | Chat API route | POST /api/chat → search + generateAnswer. Select one doc or collection. | API returns answer + citations | 1 | Done
T32 | 5 | 32 | 2026-11-25 | Web UI & Chat | Chat UI | Message list, input box, loading state, error message. | Chat with a PDF in browser | 1 | Done
T33 | 5 | 33 | 2026-11-26 | Web UI & Chat | Clickable citations | Citation chips open PDF at page (#page=N) via protected file route. | Click opens correct page | 1 | Done
T34 | 5 | 34 | 2026-11-27 | Web UI & Chat | Streaming responses | Stream tokens to UI if feasible (skip if it eats time). | Answer appears progressively | 1 | Not Started
T35 | 5 | 35 | 2026-11-28 | Web UI & Chat | Buffer / review | Catch up, commit. First full demo to yourself. | Week 5 complete & committed | 1 | Not Started
T36 | 6 | 36 | 2026-11-29 | Auth & Privacy | Authentication | Auth.js credentials provider, bcrypt-hashed passwords, register + login pages. | Can register & log in | 1 | Not Started
T37 | 6 | 37 | 2026-11-30 | Auth & Privacy | Protect routes | Middleware for pages + session checks in API routes. | Logged-out user redirected | 1 | Not Started
T38 | 6 | 38 | 2026-12-01 | Auth & Privacy | Scope data by user | Every query filters by user_id: documents, search, conversations. | Search only hits own chunks | 1 | In Progress
T39 | 6 | 39 | 2026-12-02 | Auth & Privacy | Secure file serving | File route checks ownership before streaming the PDF. | Other user's file returns 403 | 1 | In Progress
T40 | 6 | 40 | 2026-12-03 | Auth & Privacy | Privacy test | Create users A & B; try to access each other's docs, chats, citations. | All cross-access attempts fail | 1 | In Progress
T41 | 6 | 41 | 2026-12-04 | Auth & Privacy | Delete document | Delete file from disk + chunks/embeddings (ON DELETE CASCADE). | No orphan chunks remain | 1 | In Progress
T42 | 6 | 42 | 2026-12-05 | Auth & Privacy | Buffer / review | Catch up, commit. | Week 6 complete & committed | 1 | Not Started
T43 | 7 | 43 | 2026-12-06 | History & Providers | Conversation history | Save conversations & messages; sidebar list; reopen old chats. | Old chat reloads | 1 | Not Started
T44 | 7 | 44 | 2026-12-07 | History & Providers | Follow-up questions | Include last few messages as context (optionally rewrite query). | Follow-up 'what about X?' works | 1 | Not Started
T45 | 7 | 45 | 2026-12-08 | History & Providers | Document summary | Summary button: summarise doc from its chunks (map-reduce if long). | Summary shown for a doc | 1 | Not Started
T46 | 7 | 46 | 2026-12-09 | History & Providers | Error handling | Invalid files, empty PDFs, provider failure, timeouts → friendly messages. | No unhandled crashes | 1 | Not Started
T47 | 7 | 47 | 2026-12-10 | History & Providers | Qwen 2.5 via Ollama | Install Ollama, pull qwen2.5, set num_ctx ≥ 8192. Add Ollama adapter. | Answer generated locally | 1 | Not Started
T48 | 7 | 48 | 2026-12-11 | History & Providers | Provider settings screen | Admin/settings page to choose active provider; test switching end-to-end. | Switching works without code change | 1 | Not Started
T49 | 7 | 49 | 2026-12-12 | History & Providers | Buffer / review | Catch up, commit. MVP feature-complete. | Week 7 complete & committed | 1 | Not Started
T50 | 8 | 50 | 2026-12-13 | Evaluation & Deploy | Build evaluation set | 20–30 questions with known answer pages across 3–5 PDFs (Eval Log sheet). | Test set ready | 1 | In Progress
T51 | 8 | 51 | 2026-12-14 | Evaluation & Deploy | Run accuracy evaluation | Citation correctness %, 'not found' correctness, faithfulness check. | Target: ≥ 90% correct citations | 1 | In Progress
T52 | 8 | 52 | 2026-12-15 | Evaluation & Deploy | Latency measurements | Record indexing time per PDF and median response time per provider. | Target: median ≤ 5 s | 1 | In Progress
T53 | 8 | 53 | 2026-12-16 | Evaluation & Deploy | Dockerise the app | Dockerfile for Next.js; full docker-compose (app + db + storage volume). | docker compose up runs everything | 1 | Not Started
T54 | 8 | 54 | 2026-12-17 | Evaluation & Deploy | Fresh-machine test + README | Clone on clean folder/PC, follow README, fix gaps. | Works from README alone | 1 | Not Started
T55 | 8 | 55 | 2026-12-18 | Evaluation & Deploy | Report material | Screenshots, architecture diagram, results tables, demo script. | Assets ready for report | 1 | Not Started
T56 | 8 | 56 | 2026-12-19 | Evaluation & Deploy | Final review & demo rehearsal | Tag v1.0 on GitHub, rehearse demo, send to supervisor. | Demo-ready 🎯 | 1 | Not Started
Formulas:
Date = Dashboard!$C5+[Day]-1

## Eval Log
# | Date | PDF | Question | Expected page | Top-5 pages returned | Correct page in top-5? | Answer cited correct page? | Faithful (no invented facts)? | Provider | Response time (s) | Notes | Results summary | Value
1 | 2026-11-11 | lecture-notes.pdf | What is normalization in databases? | 12 | 12, 13, 4, 30, 11 | Yes | Yes | Yes | Gemini | 2.4 | Example row — replace with real tests | Tests run | 1
[12 empty] | Retrieval hit rate | 100%
[12 empty] | Citation correctness (target ≥ 90%) | 100%
[12 empty] | Faithfulness | 100%
[12 empty] | Median response time (s) (target ≤ 5) | 2.4
Row 2 is an example (blue) — overwrite it with your first real test.